## Migration Tracker
Order | Slice | Depends On | Endpoint Count | Status | Spec Doc | Validated By | Validated Date | Notes
1 | Identity | - | 3 | Code In Progress | migration_support/03_01_java_api_slice_behaviour_doc/01-identity-spec.md | muthuramanmca@gmail.com | 2026-08-02 | Foundational - no dependencies; migrate first. Spec validated in chat. Design note: migration_support/04_01_net_slice_design_note/01-identity-design.md. 04_02 (register/login/me + outbox) implemented and building green; next is 04_03 (unit tests, from the spec) and 04_04 (Java/.NET compare), then 04_05 (code review, manual gate).
2 | Flight | - | 5 | Code In Progress | migration_support/03_01_java_api_slice_behaviour_doc/02-flight-spec.md | muthuramanmca@gmail.com | 2026-08-03 | No dependencies on other slices. Spec + design note validated in chat. 04_02 implemented and building green (all 5 endpoints, entity+migration, real HoldSeat/ReleaseSeat consumers, shared AdminOnly policy). Next is 04_03 (unit tests from the spec), then 04_04 (Java/.NET compare) and 04_05 (code review, manual gate).
3 | Booking | Identity, Flight | 7 | Not Started |  |  |  | Calls FlightService.findOrThrow directly; needs both prior slices in place to build/test against
4 | Loyalty | Identity, Booking | 3 | Not Started |  |  |  | Account auto-created via PassengerRegisteredEvent (Identity); miles awarded via BookingPaidEvent (Booking) -- both event-mediated, not direct calls
5 | Notification | Booking | 1 | Not Started |  |  |  | Triggered by BookingCreatedEvent and BookingPaidEvent (Booking) -- event-mediated, not a direct call

## Legend
Status | Meaning
Not Started | Nothing done yet, not queued either
Queued for Drafting | Flagged for the next batch-drafting pass -- see migration_support/README.md
Spec In Progress | Behavior spec being drafted (03_01)
Spec Ready for Review | Spec drafted, awaiting manual validation
Rework Needed | Reviewed, gaps found -- back to drafting
Spec Validated | Confirmed correct
Design Note Ready | 04_01 design note written, awaiting review
Code In Progress | .NET implementation underway (04_02)
Code Complete | Implementation + tests done
Cutover Done | Traffic shifted for this slice